## Project Plan
Notes : You need to update the timeline on the right to reflect the current dates. Tasks must be assigned to one (and only one) owner, and each owner must have a different color associated with them (it cannot be red or green). Each requirement from the requirements document should be included, and referenced by number. You should also include any other tasks that will take time (setup, testing, documentation, etc). Each "day" on the calendar represents 2 hours of work. You should break down your tasks into chunks of 1-4 "days". The tasks below are for demonstration purposes only - replace them with your requirements and tasks. The yellow bars on the calendar represent weekends - you probably want to take those (and any breaks) into account while planning!
[6 empty] | February | [27 empty] | March | [30 empty] | April | [29 empty] | May
Requirement # | Requirement | Task # | Task | Estimate | Owner | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 2018-08-28 | 2019-09-01 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 30 | 31 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12
1 | Setup | 1.0.1 | Project plan | 2 days | Chris | bar: February 27 to February 2018-08-28
|  | 1.0.2 | Database and backend code setup in Dev env | 3 days | Chris | bar: March 2019-09-01 to March 2019-09-03
|  | 1.0.3 | NOSQL plan | 3 days | Hamza | bar: February 27 to March 2019-09-01
|  | 1.0.4 | Wireframe Desktop and Mobile | 5 days | Robin | bar: February 27 to March 2019-09-03
|  | 1.0.5 | Wireframe support | 5 days | Samar | bar: February 27 to March 2019-09-01
|  | 1.0.6 | AWS and github | 3 days | Akhil | bar: February 27 to March 2019-09-03
2 | User can visit the dictionary homepage | 2.0.1 | Home page setup UI | 2 days | Robin | bar: March 2019-09-06 to March 2019-09-07
|  | 2.0.2 | Home page backend logic | 2 days | Chris | bar: March 2019-09-06 to March 2019-09-07
|  | 2.0.3 | Integrating Front End & Backend | 3 days | Akhil | bar: March 2019-09-06 to March 2019-09-09
|  | 2.0.4 | Unit Testing | 2 days | Akhil
2.1 | User can search for words and meanings | 2.1.1 | Processing Wordnet data and Webster Data | 5 days | Hamza | bar: March 2019-09-02 to March 2019-09-03; March 2019-09-06 to March 2019-09-08
|  | 2.1.2 | Loading data to database | 2 Days | Hamza | bar: March 2019-09-09 to March 2019-09-10
|  | 2.1.3 | Create Front End for searching | 7 Days | Samar | bar: March 2019-09-02 to March 2019-09-03; March 2019-09-06 to March 2019-09-10
|  | 2.1.4 | Create front end for display of meaning | 3 days | Robin | bar: March 2019-09-08 to March 2019-09-10
|  | 2.1.5 | Create backend logic for word search | 2 days | Chris | bar: March 2019-09-08 to March 2019-09-09
|  | 2.1.6 | Create backend logic for word not found case | 1 day | Chris | bar: March 2019-09-10
|  | 2.1.7 | Integrating Front End & Backend | 3 days | Akhil | bar: March 2019-09-10
|  | 2.1.8 | Unit Testing | 2 days | Akhil | bar: March 2019-09-10
2.2 | User can listen to word pronunciations | 2.2.1 | Fetch word pronunciation using Google API | 3 days | Akhil | bar: March 2019-09-13 to March 2019-09-15
|  | 2.2.2 | Fetch word pronunciation from API and integrate | 5 days | Chris | bar: March 2019-09-13 to March 2019-09-17
|  | 2.2.3 | Add audio Links to words and cache audio | 5 days | Hamza | bar: March 2019-09-13 to March 2019-09-17
|  | 2.2.4 | UI for audio pronunciation | 5 days | Samar | bar: March 2019-09-13 to March 2019-09-17
|  | 2.2.5 | UI work | 3 days | Robin | bar: March 2019-09-13 to March 2019-09-15
|  | 2.2.6 | Create Audio listen button and test | 2 days | Robin | bar: March 2019-09-16 to March 2019-09-17
|  | 2.2.7 | Integrating Front End & Backend | 2 days | Akhil | bar: March 2019-09-16 to March 2019-09-17
2.3 | User can find example usage of words | 2.3.1 | UI Enhancements | 7 Days
|  | 2.3.3 | POS Tagging for words | 3 Days
|  | 2.3.4 | Perform semantic analysis to show sentences with context | 7 days | bar: March 2019-09-27 to March 31; April 2019-10-03 to April 2019-10-04
2.4 | User can find analytics about the words | 2.4.1 | Create log database and tables | 1 day
|  | 2.4.2 | Perform analysis on word usage | 3 Days | Hamza | bar: March 2019-09-27 to March 2019-09-29
|  | 2.4.3 | Log all words that are not found in the database | 2 days
|  | 2.4.4 | Create UI to show charts and metrics | 5 days | Samar | bar: March 2019-09-29 to March 31; April 2019-10-03 to April 2019-10-04
|  |  | Create Style Guide | 3 Days
|  |  | Application Document Prepration | 7 Days
|  |  | Test Document Creation | 3 Days | Hamza | bar: April 2019-10-17 to April 2019-10-19
|  |  | Execute User Tests | 3 days | Hamza | bar: May 2018-11-01 to May 2018-11-03
|  |  | Revise documentation | 2 days
|  |  | Execute full UAT Test Suite | 2 days | Akhil
|  |  | Prepare Presentation | 3 days | Akhil
|  |  | Wireframe preparation | 2 days
Akhil
Chris
Hamza
Robin
Samar

## Test Plan
2.1 | User can add or edit courses
1. Navigate to the "course management" screen from the main menu 2. Click on the plus icon in the top left of the scren 3. Enter the following information : CSE 611, Fall 2022, Alan Hunt 4. Click "Add Class" 5. The class should appear in the list of courses for fall 2022
1. Navigate to the "course management" screen from the main menu 2. Click on the course "CSE 611" 3. Change the instructor name to "John Doe" 4. Click "Save" 5. Verify that in the course listing, the instructor now says John Doe
2.1.1 | Verify that the "course listing" appears when the user clicks on "course management"
2.1.2 | Verify that on the course management screen, the plus icon appears. Clicking on the plus icon should bring up a modal dialog with fields for course name, course number, semester and instructor
2.1.3 | Verify that clicking on a course in the course listing brings up a modal dialong with the fields course name, course number, semester, and instructor Verify that all information in these fields is prefilled with the current values
2.1.4 | Verify that only valid semester values can be chosen for semesters verify that only valid instructors can be chosen for course instructors verify that duplicate courses create a warning